## Slide 1: 10 July 2024
TIPS
Lessons Learnt on Implementing Masterplans
By
Lunga Msengana

## Slide 2: Overview
Masterplans have created a platform for stakeholders to engage on issues affecting their industries.
There were major benefits in using a project management approach.
Reviewing lessons learnt has contributed to continuous improvement.
  Stakeholder composition for masterplans.
  The life cycle of masterplans.
  The need for a project management approach for the masterplans.
  Various lessons learnt in the implementations of masterplans.

## Slide 3: Stakeholders in Masterplans
The planning and execution of masterplans is achieved by effective relationships between various stakeholders, like:
  Government Departments
  Organised Labour
  Private Sector
  Service Providers

## Slide 4: Life Cycle of a Masterplan
Phase 5: Monitor & Control
Phase 4: Implementation
Phase 2: Development
Phase 3: Priorities & Develop Plans
Phase 1: Preparation
  Decide on the Masterplan.
  Establishing governing structures.
  Implementation of the plans within the governance framework.
  Situational analysis.
  Mapping of the “To be situation”.
  Monitoring and controlling of activities as per plans.
  Compile list of outcomes and prioritise them.

## Slide 5: The need for a project management approach
We can confine the scope of work to target specific deliverables.
Allows the teams to have a strong focus on the goals to be achieved.
We can mitigate the risks associated with the deliverables.
We can effectively manage stakeholder expectations.
It provides a platform for conflict management.
We can manage and monitor the delivery of benefits.

## Slide 6: Masterplans supported by TIPS PMU
Retail, Clothing, Textile, Footwear & Leather
Sugar
Steel
Forestry
Medical Technology
Plastics

## Slide 7: Lessons Learnt across Masterplans

## Slide 8: What worked well
They created a platform for industry players to engage each other on a regular basis on matters affecting their industries.
Methods for tracking the progress on commitments were established. This made engagements to be more objective.
There were clear plans for implementation, and these were monitored and controlled.
Leveraging on diversity since stakeholders were coming from different backgrounds.

## Slide 9: Some of the challenges
There can be issues of escalation that are beyond the implementation team’s locus of control.
Intergovernmental engagements.
Some deliverable take more time to implement due to the nature of engagements and diversity of stakeholders.
Major shakeups in one dominant company have been a risk to the masterplans.

## Slide 10: Where we can improve
Effective resourcing for masterplans in terms of finances and human resources.
Review the structures of oversight committees and working groups.
More effective ways for escalating and unblocking issues.
Narrowed focus to resolve priority challenges in an industry.

## Slide 11: Bibliography
Levin, S. & Makgetla, N. 2019. Masterplans and Industrial Policy. Policy Brief:1:2019.
Masterplan Guide

## Slide 12: THANK YOU